## Sheet1
Risk number | Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Time limited project | Running out of time and not meeting the MVP | High | High | Developers | Make sure to keep working towards the MVP and only focus on extensions after providing the MVP | Make use of the kanban board, keeping up with the burndown chart, which will allow you to keep ontrack to finish the MVP ontime
2 | Broken machine | Machine goes offline | Low | High | Developers | Pull files from VCS on another machine to recreate progress | Make frequent small commits so that in the case that a machine does go offline you have up to date progress available to seemlessly keep working on another device
3 | Broken code | Errors in the code | High | High | Developers | Revert to most recent stable version | Make sure to get above 80% testing coverage in order to cover the majority of the code
4 | Hand injury | Developer sustains hand injury | Very low | Very High | Developers | Obtain speech to text application in order to complete the project in time | Avoid excess straining of hands
5 | CSRF | CSRF Key not correctly hidden | Very low | Very High | Developers | Take the site down and correctly hide the key after changing it in order to remove the vulnerabilities | form.hidden_tag() - must be included in your front-end html on any page which contains a post method in order to prevent others from having access